## Template
Project Name:
UW-Madison Project Classification - Impact Assessment
Risk Factors To Consider | Low Impact (0) | Medium (2) | High Impact (4) | Rating | Weight | Score | Scoring Guidance | Proposal Notes
Q 13: Creating a service similar to one in the Service Inventory or replacing/significantly modifying an existing service? | No |  | Yes | 0
Q 14: New service could be used by other campus units? | No |  | Yes | 0
Q 15: Similar projects in Project Portfolio? | No |  | Yes | 0
Q 17: Estimated total IT cost to implement? | Less than $100,000 | $100,000 to $499,999 | $500,000 or more | 0 |  |  | <Provide guidance on how to calculate; ex. hours to dollars conversion>
Q 18: Estimated hours of UW-Madison IT staff time to implement? | Less than 500 hours | 500 to 4,999 hours | 5,000 hours or more | 0 |  |  | <Provide a formula>
Q 19: Total IT cost to operate/maintain the solution for the first three years? | Less than $100,000 | $100,000 to $499,999 | $500,000 or more | 0
Q 21: Is the project fully funded? | Yes |  | No | 0
Q 22: Increase capacity of existing UW-Madison infrastructure? | No |  | Yes | 0
Q 23: Scope of project impact? | Department/divisional | Two or more divisions | Central/campus-wide/UW System | 0
Q 24: Roles of end users/consumers impacted? | Department staff, faculty/instructors only | Divisional staff, faculty/instructors, limited (credit or non-credit) student cohort or external partners | Large campus-wide faculty/instructors, staff, (credit or non-credit) student cohort, or the public | 0
Q 25: Total number of people directly or indirectly affected by the solution | Less than 1,000 | 1,000 to 9,999 | 10,000 or more | 0
|  |  | Overall Score | 0
Low impact | zero to fifteen (0-15) | Project Classification: ___________________________________
Medium Impact | sixteen to twenty-nine (16 - 29)
High Impact | thirty plus (30 +)
Maximum points = 44

## Test_Moodle
Project Name: Moodle
UW-Madison Project Classification - Impact Assessment
Risk Factors To Consider | Low Impact (0) | Medium (2) | High Impact (4) | Rating | Weight | Score | Scoring Guidance | Proposal Notes
Duplicate services in Service Catalog | No |  | Yes | 4
New solution could be used by other campus units | No |  | Yes | 4
Similar projects in Project Portfolio | No |  | Yes | 0
Estimated total IT cost to implement | Less than $100,000 | $100,000 to $499,999 | $500,000 or more | 2 |  |  | <Provide guidance on how to calculate; ex. hours to dollars conversion>
Estimated hours of UW-Madison IT staff time to implement | Less than 500 hours | 500 to 4,999 hours | 5,000 hours or more | 4 |  |  | <Provide a formula>
Total IT cost to operate/maintain the solution for the first three years | Less than $100,000 | $100,000 to $499,999 | $500,000 or more | 4
Increase capacity of UW-Madison IT infrastructure | No |  | Yes | 0
Scope of project impact | Department/divisional | Two or more divisions | Central/campus-wide/UW System | 4
Roles of end users/consumers impacted | Department staff, faculty/instructors only | Divisional staff, faculty/instructors, limited (credit or non-credit) student cohort or external partners | Large campus-wide faculty/instructors, staff, (credit or non-credit) student cohort, or the public | 4
Total number of people directly or indirectly affected by the solution | Less than 1,000 | 1,000 to 9,999 | 10,000 or more | 4
|  |  | Overall Score | 30
Low impact | zero to thirteen (0-13) | Project Classification: _____High Impact______________________________
Medium Impact | fourteen to twenty-five (14 - 25)
High Impact | twenty-six plus (26 +)
Maximum points = 40

## Test_CoE Data Storage
Project Name: College of Engineering Data Storage
UW-Madison Project Classification - Impact Assessment
Risk Factors To Consider | Low Impact (0) | Medium (2) | High Impact (4) | Rating | Weight | Score | Scoring Guidance | Proposal Notes
Duplicate services in Service Catalog | No |  | Yes | 4
New solution could be used by other campus units | No |  | Yes | 0
Similar projects in Project Portfolio | No |  | Yes | 0
Estimated total IT cost to implement | Less than $100,000 | $100,000 to $499,999 | $500,000 or more | 0 |  |  | <Provide guidance on how to calculate; ex. hours to dollars conversion>
Estimated hours of UW-Madison IT staff time to implement | Less than 500 hours | 500 to 4,999 hours | 5,000 hours or more | 0 |  |  | <Provide a formula>
Total IT cost to operate/maintain the solution for the first three years | Less than $100,000 | $100,000 to $499,999 | $500,000 or more | 0
Increase capacity of UW-Madison IT infrastructure | No |  | Yes | 4
Scope of project impact | Department/divisional | Two or more divisions | Central/campus-wide/UW System | 0
Roles of end users/consumers impacted | Department staff, faculty/instructors only | Divisional staff, faculty/instructors, limited (credit or non-credit) student cohort or external partners | Large campus-wide faculty/instructors, staff, (credit or non-credit) student cohort, or the public | 2
Total number of people directly or indirectly affected by the solution | Less than 1,000 | 1,000 to 9,999 | 10,000 or more | 2
|  |  | Overall Score | 12
Low impact | zero to thirteen (0-13) | Project Classification: ____Low Impact______________________________
Medium Impact | fourteen to twenty-five (14 - 25)
High Impact | twenty-six plus (26 +)
Maximum points = 40

## Test_Event Mgmt System
Project Name: Event Management System
UW-Madison Project Classification - Impact Assessment
Risk Factors To Consider | Low Impact (0) | Medium (2) | High Impact (4) | Rating | Weight | Score | Scoring Guidance | Proposal Notes
Duplicate services in Service Catalog | No |  | Yes | 0
New solution could be used by other campus units | No |  | Yes | 4
Similar projects in Project Portfolio | No |  | Yes | 0
Estimated total IT cost to implement | Less than $100,000 | $100,000 to $499,999 | $500,000 or more | 4 |  |  | <Provide guidance on how to calculate; ex. hours to dollars conversion>
Estimated hours of UW-Madison IT staff time to implement | Less than 500 hours | 500 to 4,999 hours | 5,000 hours or more | 2 |  |  | <Provide a formula>
Total IT cost to operate/maintain the solution for the first three years | Less than $100,000 | $100,000 to $499,999 | $500,000 or more | 2
Increase capacity of UW-Madison IT infrastructure | No |  | Yes | 0
Scope of project impact | Department/divisional | Two or more divisions | Central/campus-wide/UW System | 2
Roles of end users/consumers impacted | Department staff, faculty/instructors only | Divisional staff, faculty/instructors, limited (credit or non-credit) student cohort or external partners | Large campus-wide faculty/instructors, staff, (credit or non-credit) student cohort, or the public | 4
Total number of people directly or indirectly affected by the solution | Less than 1,000 | 1,000 to 9,999 | 10,000 or more | 4
|  |  | Overall Score | 22
Low impact | zero to thirteen (0-13) | Project Classification: _____Medium Impact_____________________________
Medium Impact | fourteen to twenty-five (14 - 25)
High Impact | twenty-six plus (26 +)
Maximum points = 40

## History 2
Project Name:
UW-Madison Project Classification - Impact Assessment
Risk Factors To Consider | Low Impact (0) | Medium (1) | High Impact (2) | Score | Notes
Mandate/Compliance | Discretionary project - No Federal / State or UW-Madison / UW System mandate | Project responds to UW-Madison / UW System Mandate, or Policy | Project responds to Federal or State, other formal governing bodies Mandate | 0
Estimated Benefits (Looking for a sense of the absolute value of the impact, whether negative or positive.) | No Cost savings, Efficiencies or Consolidation | Moderate cost savings, efficiencies, brand or revenue enhancement. | Significant cost savings, efficiencies, brand or revenue enhancement. | 0
Investment Type | Run - Maintain current service offer | Grow - Modify or enhance information systems and services to optimize performance | Transform - Implement new technologies and processes that fundamentally promote change | 0
Solution Complexity | Solution is well defined and/or minimal problems are expected | There is more than one approach identified to achieving the project goal and/or moderate problems are expected | The solution is not known or only vaguely defined | 0
Scope of Implementation Commitment | Department/Divisional | Centralized (2 or more divisions) | Central/Campus-Wide/UW System | 0
Scope of End User Impact | Department staff / faculty only | Divisional staff / faculty, limited student cohort or external parties | Large campus-wide faculty, staff, or student cohort or greater | 0
Nature of End User Impact (Change Mgmt) | Minimal change in process; minimal training, minimal risk to post-implementation operations | Significant business process change; some risk to post-implementation operations | Adds or eliminates positions and/or significantly changes position duties and responsibilities; implies significant risk to post-implementation operations | 0
Time Sensitivity | Not bounded by specific deadlines | Clear benefits from timely implementation | Critical deadlines and significant associated risk | 0
Lifecycle | Short-lived pilot | Moderate (1-3 year) lifecycle commitment | Long (3+ years) expected lifecycle commitment OR rapidly evolving product solution space | 0
Risk Mitigation | Project is not being undertaken to mitigate any identifiable risks | Project to mitigate targeted risks with moderate impact | Project to mitigate significant risks such as data privacy or security breach, damage to university reputation, campus-wide service interruption | 0
Funding | Funding source known and available or not required | Some funding available | Funding not identified | 0
|  |  | Overall Score | 0
Project Type Small | zero to seven (0-7) | Project Classification: ___________________________________ |  |  | Explanation for Project Type Selected (Optional):
Project Type Medium | nine to fourteen (8-14)
Project Type Large | fifteen plus (15)+

## History 1
Brief Summary of Test Case:
UW-Madison Project Classification - Impact Assessment
Risk Factors To Consider | Low Impact (0) | Medium (1) | High Impact (2) | Score
Mandate | Discretionary project - No Federal / State or UW-Madison / UW System mandate | Project responds to UW-Madison / UW System Mandate, or Policy | Project responds to Federal or State, other formal governing bodies Mandate | 2
Estimated Benefits | No Cost savings, Efficiencies or Consolidation | One of the following: Cost savings, Efficiencies, Brand or Revenue Enhancement. | Two or more: Cost savings, Efficiencies, Brand or Revenue Enhancement. | 2
Funding | Funding source known and available or not required | Some funding available | Funding not identified | 2
Investment Type | Run - Maintain current service offer | Grow - Modify or enhance information systems and services to optimize performance | Transform - Implement new technologies and processes that fundamentally promote change | 2
Solution Complexity | Solution is well defined and/or minimal problems are expected | There is more than one approach identified to achieving the project goal and/or moderate problems are expected | The solution is not known or only vaguely defined | 2
Potential Scale of Involvement | Department/Divisional | Centralized (2 or more divisions) | Central/Campus-Wide/UW System | 2
Scope of End User Impact | Department staff / faculty only | Divisional staff / faculty, limited student cohort or external parties | Large campus-wide faculty, staff, or student cohort or greater | 2
Project Visiblity and Risk | No visibility outside department/division | Limited visibility to campus or external to campus | Visibility to students and/or external to campus | 2
|  |  | Overall Score | 16
Project Type I | zero to five (0-5) | Project Classification: ____________EXEC Level 3_______________________
Project Type II | six to eleven (6-11)
Project Type III | twelve to sixteen (12-16)